## Budget
Construction budget: budget vs committed vs spent
Yellow cells are inputs. Example figures are a made-up 48-unit apartment project at month 10 of 18. Mark contingency lines with yes.
Free from proformakit.com, where the same template runs online
Category | Line item | Budget | Committed | Spent | Forecast | Variance | % committed | % spent | Left to commit | Contingency? | Check
Land & acquisition | Purchase price | 2280000 | 2280000 | 2280000 | 2280000
Land & acquisition | Closing costs and title | 84000 | 84000 | 84000 | 84000
Land & acquisition | Due diligence and surveys | 36000 | 36000 | 36000 | 36000
Hard costs | Site work and utilities | 864000 | 801900 | 527271 | 873900
Hard costs | Foundations and structure | 2688000 | 2494800 | 1640398 | 2718800
Hard costs | Envelope and roofing | 1344000 | 1247400 | 820199 | 1359400
Hard costs | Mechanical, electrical, plumbing | 1920000 | 1782000 | 1171713 | 1942000
Hard costs | Interiors and finishes | 1824000 | 1692900 | 1113127 | 1844900
Hard costs | General conditions and GC fee | 960000 | 891000 | 585856 | 971000
Soft costs | Architecture and engineering | 551000 | 448400 | 306112 | 539600
Soft costs | Permits and impact fees | 319000 | 259600 | 177222 | 312400
Soft costs | Legal and accounting | 116000 | 94400 | 64444 | 113600
Soft costs | Insurance and builder's risk | 145000 | 118000 | 80556 | 142000
Soft costs | Property taxes during construction | 101500 | 82600 | 56389 | 99400
Soft costs | Marketing and lease-up | 217500 | 177000 | 120833 | 213000
Contingency | Hard cost contingency | 384000 | 256000 | 234342 | 320000 |  |  |  |  | yes
Contingency | Soft cost contingency | 96000 | 64000 | 58586 | 80000 |  |  |  |  | yes
Financing & interest | Construction interest | 918230 | 33837 | 33837 | 918230
Total
Summary
Budget
Committed in signed contracts
Spent
Forecast at completion
Variance (forecast minus budget)
Contingency left to commit