## Draw request
Construction draw request
Costs to date by budget line, less the equity paid in and earlier draws, is what this draw asks for. Yellow cells are inputs; send it with the invoices, lien waivers and photos.
Free from proformakit.com, where the same template runs online
Project | Pecan Row Apartments (example)
Draw | Draw 4
Period ending | 2026-11-15
Budget line | Budget | Costs to date | % complete | Balance to finish
Land & acquisition | 2400000 | 2400000
Hard costs | 9600000 | 5858564
Soft costs | 1450000 | 805556
Contingency | 480000 | 292928
Financing & interest | 918230 | 33837
Total
This draw
Total costs to date
Less equity paid in |  | 5196880
Less earlier draws |  | 2983311
Amount requested this draw

## Cover sheet
Draw request cover sheet
One page on top of the package so the lender knows what it is looking at. Yellow cells are inputs.
Free from proformakit.com, where the same template runs online
Project name | Pecan Row Apartments (example)
Loan or project number
Draw | Draw 4
Period ending | 2026-11-15
Amount requested
Anything unusual in this draw
Contact for questions (name and phone)
Attach, as your lender asks
[ ] Pay application from the general contractor (AIA G702 and G703 or the lender's equivalent)
[ ] Invoices for soft costs, and paid invoices with copies of checks for anything you are reimbursed for
[ ] Lien waivers from the contractors and suppliers paid with the previous draw
[ ] Photos of the line items completed this period
[ ] Signed change orders, if any
[ ] Evidence of insurance for materials stored off site, if any