## Draw schedule
Construction loan draw schedule
Yellow cells are inputs. The example is a made-up project: one planned draw per month from its pro forma, interest included.
Free from proformakit.com, where the same template runs online
Draw | Date | Amount | Status | Funded and submitted to date | Loan left | Loan
Draw 1 | 2026-08-15 | 650542 | Funded |  |  | Construction loan amount | 9651349
Draw 2 | 2026-09-15 | 1129595 | Funded
Draw 3 | 2026-10-15 | 1203174 | Funded |  |  | Summary
Draw 4 | 2026-11-15 | 1210694 | Submitted |  |  | Funded
Draw 5 | 2026-12-15 | 1151742 | Planned |  |  | Submitted, waiting on the lender
Draw 6 | 2027-01-15 | 1033928 | Planned |  |  | Planned, not yet requested
Draw 7 | 2027-02-15 | 871959 | Planned |  |  | Loan left after funded and submitted
Draw 8 | 2027-03-15 | 685879 | Planned |  |  | Planned draws beyond what is left
Draw 9 | 2027-04-15 | 498633 | Planned
Draw 10 | 2027-05-15 | 333321 | Planned |  |  | Check
Draw 11 | 2027-06-15 | 210390 | Planned
Draw 12 | 2027-07-15 | 145188 | Planned
Draw 13 | 2027-08-15 | 57031 | Planned
Draw 14 | 2027-09-15 | 57388 | Planned
Draw 15 | 2027-10-15 | 57747 | Planned
Draw 16 | 2027-11-15 | 58107 | Planned
Draw 17 | 2027-12-15 | 58471 | Planned
Draw 18 | 2028-01-15 | 58836 | Planned
Draw 19 | 2028-02-15 | 59204 | Planned
Draw 20 | 2028-03-15 | 59574 | Planned
Draw 21 | 2028-04-15 | 59946 | Planned

## Draw request
Construction draw request
Costs to date by budget line, less the equity paid in and earlier draws, is what this draw asks for. Yellow cells are inputs; send it with the invoices, lien waivers and photos.
Free from proformakit.com, where the same template runs online
Project | Pecan Row Apartments (example)
Draw | Draw 4
Period ending | 2026-11-15
Budget line | Budget | Costs to date | % complete | Balance to finish
Land & acquisition | 2400000 | 2400000
Hard costs | 9600000 | 5858564
Soft costs | 1450000 | 805556
Contingency | 480000 | 292928
Financing & interest | 918230 | 33837
Total
This draw
Total costs to date
Less equity paid in |  | 5196880
Less earlier draws
Amount requested this draw